| Led by Group | Page in SP | Themes | Action | Progress |
| --- | --- | --- | --- | --- |
| Co. Chairman Co. Secretary Co. Executive | 22 a | Structure & overall governance | Total review of Co. Bye-laws in order to implement the recommendations of the Strategic Plan. | New bye-laws implemented circa April O7. Ongoing review of these as need arises. |
| Co. Executive Co. Committee | 22 b | Structure & overall governance | Merge positions of Chairman and Central Council Delegate into one post. | Implemented circa April 07. |
| Co. Executive Co. Committee | 22 c | Structure & overall governance | CAM becomes a non-voting member of the Management Committee. | Implemented circa April 07. |
| Co. Executive | 22 d | Structure & overall governance | Appoint a working committee to: Review present structures of governance in Antrim CLG including all existing committees and the three divisional boards, highlighting their strengths and weaknesses. Produce a model of governance that streamlines structures, reduces bureaucracy and works more efficiently. | There have been changes made to the County Executive in 2007 to streamline governance plus the review of structures and overall governance is on going. Draft terms of reference have been drawn up with reference to a review of all employed staff, CAM, HDM, FDM and secretaries to be approved. |
| PRO Club Aontroma | 22 e | Communications | Establish PR, Communications and Marketing Committee with strong links to Club Aontroma. | Committee well established. Main achievements: Saffron Og on-line, Yearbook (winner of Mc Namee Award , national GAA award) and Presentation Dinner. |
| PR Committee PRO CCC | 22 f | Communications | Production of an annual county information manual released in January that includes contacts for chairpersons, secretaries, youth officers, coaching officers and team management from youth to senior level. | The PR Committee feel as this information is available on the County Website the cost of producing the manual would be a waste of money, plus website has been extremely successful and will continue to be so as a point of contact for Antrim Gaels at home and abroad. |
| PR Committee PRO | 22 g | Communications | Annual County Yearbook released before Christmas that reviews Gaelic games in Antrim the previous year. | The yearbook committee, of which Alex Emerson is the editor, is already at work on the 2007 production. |
| Grounds Committee | 23 | Infrastructure | Facilities Audit: Carry out an audit of all facilities for Gaelic games in Antrim (GAA, education, council and other) to establish who provides what, where and to what standard / quality. | Audit completed by Ray Compston (Grounds Committee) re: current facilities available circa Dec 06. Review and update for 2007 is ongoing. |

| Led by Group | Page in SP | Themes | Action | Progress |
| --- | --- | --- | --- | --- |
| Oifigeach Cultuir | 24 a | Culture & Heritage | Club: Have a Cultural Officer appointed to every club. | To date, October 2007, 45% of clubs have a cultural officer, a huge improvement on 2006 but further progress is sought to achieve this target. |
| Cultural Officer | 24 b | Culture & Heritage | Ensure “St. Patrick’s Day language collections” are taken up in every club area to fund Gaeltacht bursaries for local children. | 4 different scholarships are available through the 3 Divisional Boards for students to attend Irish Colleges in Summer 2008, also at Easter 2008, the Roger Casement Memorial Scholarship will be launched. NB It is felt that the language collection envisaged should not be taken up as it clashes with other Irish language collections on that day. |
| Co. Management Co. P.R. Committee | 25 a | Culture & Heritage | Cultural Festivals: Engage with organizers of existing festivals in Antrim (e.g. Feile an Phobail) to provide GAA support to these events. | Each year an under age blitz (U13) is held in Casement Park as part of a Feile. Names are taken in advance and then teams are sorted by PJ O’ Hare (GPO). All participants receive a jersey sponsored by O’Neill’s. There is also a Poc Fada held during the Feile and some of the juvenile teams’ of the local GAA clubs walk in the Feile Parade. |
| Oifigeach Cultuir And divisional officers with support from club Cultural Officers | 25 b | Culture & Heritage | Gaelic Games: As a means of recognizing the fact that Antrim has a very large number of Irish speakers, hold a special sporting competition, focused on rounders (so as to be as inclusive as possible), in celebration of this fact. | 2007 saw the exciting development of the establishment of Laochra Loch Lao, a GAA club for Irish Speakers. The cumann entered a team to play in the Comortas Peile na Gaeltachta which recognised the fact that gaeltacht status has been achieved in Antrim. |
| Executive Committee | 26 a | Integration & Equality | Representation: Establish an Integration and Equality sub-committee with representatives from the Camogie, Ladies’ Football, Handball and Rounders County Boards. This committee should also include members who have a background in catering for those with disabilities or who have experience in equality issues. | Leas Cathaoirleach and Leas Runai appointed as representatives to the Ulster Council work group responsible for progressing Integration and Equality within all counties in Ulster. Progress entirely dependent on progress at National and Provincial level. The monthly Ladies’ Football meetings are now held in Casement Park. In 2007 the Junior Ladies’ Football Final was played at Casement Park, the first time that has happened. |
| County Committee | 26 b | Integration & Equality | Integration: Delegates from Ladies’ Football, Camogie, Rounders and Handball sitting on the County Board. | Delegate of Handball Committee already member of County Committee. |
| County Committee | 26 c | Integration & Equality | Structure: A new portfolio (officer) for Integration and Equality at Management Committee level. | Leas Runai appointed to this position in “shadow” role until full implementation of Integration and Equality occurs. |
| County Executive CAM | 27 a | Coaching & Games Development | To further develop the roles of CAM, HDM and FDM. | With regard to HDM and FDM, their professional development is ongoing, to enable them to deliver the different programmes emanating from Croke Park and Ulster Council as part of Grassroots to National Plan (GNP). As part of the Ulster Council’s Modernisation programme, all these positions are currently being reviewed. |
| CAM County Executive | 27 b | Coaching & Games Development | To employ 2 full-time GPOs for the county. | 2 Full time GPOs are employed working in the post primary sector, with clubs and Cumann na mBunscol. |

| Led by Group | Page in SP | Themes | Action | Progress |
| --- | --- | --- | --- | --- |
| Co. Executive, Coaching & Games Development Committee Cumann na mBunscoil | 27 c | Coaching & Games Development | Coach Education: Investigate the feasibility of employing a full-time Coaching Education Officer within the county. | To be carried forward to 2008. |
| Ulster Council – RDO/HDM/FDM | 28 a | Coaching & Games Development | Coaching courses at all the above levels are available every quarter (every 3 months) in all regions. | Foundation and Child Protection courses are available to clubs. Level 1 Hurling and Football, one of each to be held before end of 2007 and another one of each to be held before end of April 2008. Details will be on coaching calendar plus other dedicated courses for hurling and football ie: goalkeeping courses. |
| CAM/County Executive | 28 b | Coaching & Games Development | Fixtures: An All-County fixtures booklet will be completed and agreed by February 2007. | Electronic version of proposed fixtures produced and circulated to all relevant bodies and posted on Website. Decision taken not to produce hard copy due to unavoidable changes having to be made on a frequent basis. |
| FDM/HDM Bord na n’Og | 28 c | Coaching & Games Development | U8, U10 and U12 teams will participate in Go Games activities. | Go Games have been held each month in South Antrim (SA) from March 2007, alternating between hurling and football. There have also been U8/U10/U12 blitzes. Go Games have been held in South West (SW) and while in North Antrim (NA) there have been conditioned games blitzes (x13). Some clubs in each division also have hosted very successful blitzes. |
| FDM/HDM/ Coaching & Games Development Committee Ulster Council RDO | 28 d | Coaching & Games Development | Club Development: Workshops for Coaching and Games’ Development. | Workshops have been held in both hurling and football for club coaches on a divisional and all county basis plus a Coaching Calendar will be produced with details of the courses for 2007/08. |
| Referees Committee | 29 a | Coaching & Games Development | Referees: Referees Committee to be renamed ‘Referees Development Committee’ with responsibility for the overall development of refereeing within the county. | Match officials are proactive in the county administering the guidelines as set by the National Referees’ Committee. |
| Management Committee County Board | 29 b | Coaching & Games Development | Referees Coordinator becomes a member of the Management Committee. | This occurs by default (Gerry McClory) and this has not been considered appropriate or necessary by current management or County Committee. |
| HDM/FDM Referees Coordinator Referees Development Comm | 29 c | Coaching & Games Development | Establish a referee-recruitment programme tied into the Coaching and Games Development programme. | Referee tutors are attending level 1 coaching courses to discuss rules etc. Referee-recruitment programme is ongoing within the county. |
| HDM/FDM Referees Coordinator Referees Development Comm Cumann na mBunscoil Bord na n’Og | 30 a | Coaching & Games Development | Establish the Young Whistlers programme as a central theme to the county education and coaching and games development programme. | Young Whistlers’ programme has been established in some primary schools and a new course ran in Jan 07 for club Young Whistlers, will be run again in 2008. |

| Led by Group | Page in SP | Themes | Action | Progress |
| --- | --- | --- | --- | --- |
| Games Administration Committee N. Antrim, SW Antrim | 30 b | Rural Development | Fixtures: Draw up an annual fixtures list that provides senior club players with games on a regular basis. | Fixtures list was available at an all county level on the county website, N Antrim and S Antrim produced divisional fixture booklets for 2007 including senior and juvenile. SW put fixtures onto Divisional website on a fortnightly basis. |
| Executive Committee, N. Antrim, SW Boards | 31 a | Rural Development | Governance/Administration: Investigate the feasibility of an appointment of an Education Officer to oversee the N & SW Antrim areas. This person would: Acquire and disseminate information about finances, grants & good practice that would help develop clubs. He/she would assist with applications for grants, planning etc. Organise workshops that help inform clubs how to operate more smoothly and informs about development plans, infrastructure etc. Liaise with governing bodies of GAA. Visit all schools to promote gaelic games amongst pupils and staff. Organise workshops/visits that highlight e.g. the effects of alcohol or drug abuse. Help clubs, schools & colleges to organize games, blitzes, summer camps etc. | In the absence of an Education Officer the following actions have been progressed. All primary schools in SW and NA are receiving GAA coaching. The school coaches are promoting our games and are organizing Go Games during their coaching blocks where possible. Ulster Council had a Provincial Convention on 20th Oct to cover relevant areas plus others will be held within the county ie: Valuing Volunteers was held on 16 th Oct. NA had an U14 Summer Camp. Successful Cul Camps were held in Summer of 2007 in all of the divisional areas, with an increase in numbers attending over 2006. |
| Management N & SW Antrim Boards Handball Committee | 31 b | Rural Development | Facilities: Investigate the feasibility of building two large indoor facilities that are centrally located; one in North and one in SW Antrim. Each building would have a large hall, changing facilities, handball courts and meeting room and may be linked to education. | Indoor facility at Dunloy is at planning stage. County report on infrastructure has highlighted Garron Tower as a possible site. |

| Led by Group | Page in SP | Themes | Action | Progress |
| --- | --- | --- | --- | --- |
| Management N & SW Antrim Boards Communications and PR Comm | 31 c | Rural Development | Encourage gaelic clubs and their communities to look for and secure all-weather facilities from their local councils. | Clubs have been using the Council astro-facility at Ballycastle for U13 league, it will be used again in 2008. Lack of all weather facilities in Moyle Council area. Some SW Clubs use Antrim Forum. There is an astro- facility at Erin’s Own GAC. |
| Management, N and SW Antrim | 31 d | Rural Development | Research: Appoint a placement student or research student to carry out research about demographics and trends in rural areas of Antrim. | This has been completed on an all county basis by Eamon Prenter’s company (Strattan, Reynolds Chartered Surveyors) as part of draft guidelines to be used when deciding what infrastructure the county will develop for training facilities and has been presented to all relevant units for further discussion. |
| CAM Executive Committee Ulster Council | 32 | Belfast | Strategy: Establish an Urban Development Scheme in Belfast similar to Derry City Council. | A meeting of the various parties is imminent to progress this initiative. 5 additional coaches are working in Antrim funded by DENI. |
| Coaching Officer/ Development Managers County Board County Board Education Officer | 33 a | Schools | Development of coaching in schools: Establish a club/school link education officer within County Management structure. | Extensive coaching programme already in place for schools (just over 100 schools being covered) and ongoing. The Ulster Council School Coaches (x5) began work in Antrim on 5/11/07.As part of their remit they have to expand club/school links. The Antrim School coaches (x 6) encourage children to join local their clubs. Where possible, coaches will promote after school activity. With reference to Club/School Link Education Officer, see 27 C above. |
| Coaching Officer | 33 b | Schools | Annual Year 8 competition possibly floodlit at Casement Park, to be started during year 1 of plan. | Football final was played under lights. There were also indoor and outdoor year 8 hurling blitzes. |
| Development Managers/ Coaching Officer | 33 c | Schools | Devise a proactive coaching framework for all employed coaches including GAA education, games promotion, developing club/school links, accountability etc. | Coaches are given lesson plans for P1 to P7 covering Fundamentals, Basic Skills of Hurling, Gaelic and Camogie, Skill Development and Go Games. |
| Development Managers | 33d | Schools | Every Primary School in County provided with coaching for at least 12 weeks per year | Achieved in 2006/07 and in 2007/08 schools will receive on average 16 weeks coaching |
| Coaching and Games Committee | 33 e | Schools | Promote positive discrimination in coaching re: specifically for female teachers/teaching students. | One of the Antrim school coaches for 2007/2008 is female plus two of the Ulster Council School coaches who will be working in Antrim are female. Teachers, male or female are encouraged to get involved with sessions when coaches are in the schools. Third Level Colleges are providing Foundation courses for football and hurling. These are available to all students. |
| Education Officer Staff Coaching officer Divisional Boards Development Managers | 34 a-f | Club/School Links | To develop and promote club/school links. | Club/School Link Officer within county management structure, not in place after Convention 2006. As part of the Club Development Conference on 20th October 07, one of the workshops focused on ‘Developing and Sustaining Club School Links’ which provided step by step advice on forming strong links with local schools. Conference was attended by Antrim County Officers and individual club members. Some clubs have already established club/school links. The club/school link is an important area to be addressed and will require localized approaches in each of the Divisional Boards. There is progress towards developing closer working relationships with Cumann na mBunscol, Schools, County and Divisional Boards. |
| Coaching Officer / Development Managers | 35 a | Schools | Develop club/school links with those schools not normally associated with Gaelic sports | In 2007/08 the Antrim Schools’ Coaching Programme, coaches have been in nine Integrated Primary Schools and one Post Primary Integrated College. The Ulster Council Schools’ Coaches working in Antrim have begun to provide Controlled Schools with taster sessions of Fundamentals, Hurling and Football and to develop links. |
| County Board Ulster Colleges Vocational Schools | 35 b | Schools | Action: Establish a ‘Think Tank’ approach to guide future development over span of plan. | See 35c below ref St Mary’s CBS. |
| C N mB Ulster Colleges Vocational schools Coaching and Games Committee Teachers in post primary schools | 35 c | Schools | Emphasis on strengthening/consolidating Year 8 pupil participation/competition. Win Mageean /Mac Rory/ Mc Larnon Cups during life of plan. | Year 8 football league established as well as indoor hurling blitz. Two Antrim teams contested the Mageean Cup Final in 2007. St Mary’s CBS were the winners with CPC runners up. Rathmore GS, an Antrim school won the Casement Cup (B Hurling) in 2007. St Mary’s CBS has produced a development plan which involves participation in the following A grade competitions, Year 8, Year 9, Year 10, and Year 12 in 2007/08. They intend to enter the Mac Rory Cup in 08/09. Success of La Salle and Rathmore in recent years in the Mc Larnon Cup has helped the County Minor Football team. Edmund Rice College CBS won the Nolan Cup (C Football). |
| County Board | 35 d | Schools | Create an overall Schools committee within the County. Utilise facilities at Colleges of Education/Universities for benefit of 2nd level students. | In 2007 the Antrim Coaching and Games committee has representatives from Cumann na mBunscol, Vocational Schools and Colleges. NB: The other members of Coaching and & Games committee include: , NA Chairman, SA Secretary, SW Chairman Youth Officer, FDM and HDM.. Alternatively, the County has provided resources ie Casement Park for finals, Woodlands for C Hurling Blitz. The Post Primary Antrim All Stars’ scheme has been initiated with each successful nominee receiving an Antrim jersey. |
| County Executive /County Committee | 36 a | Finance | Finance Committee: Establish Antrim County Board Finance Committee – chaired by County Treasurer. | Had been implemented in 2006, but has been superceded by establishment of a fund-raising committee this year which organized the Sweep and Race Day. To be reviewed at the end of 2007. |
| Finance Committee Club Aontroma | 36 b | Finance | Appraisal: Carry out an appraisal of the current position regarding finances and assets of the county. | Ongoing and almost completed with co-operation from Maneely McCann accountants, Co Treasurer and CAM. Proposals to be presented to County Executive and County Committee in the coming months. |
| Finance Committee | 36 c | Finance | Procedures and Budget: Draw up financial systems and procedures with strict authorization limits, to include sourcing, receiving and recording income and control of expenditure. | This is to be progressed upon completion of 36 b. |
| Finance Committee | 36 d | Finance | Financial Plan: Produce a financial plan for the next five years, giving detailed projections of income and expenditure and the financial implications of implementing strategic plan. | This will be dependent on 36 b and 36c Target date for this to be completed, is July 08. |

| Led by Group | Page in SP | Themes | Action | Progress |
| --- | --- | --- | --- | --- |
| Finance Committee County Development Officer Club Aontroma | 36 e | Finance | Sources of Funding: Identify and exploit all possible funding opportunities. Widen existing avenues of funding, research new avenues and adopt a proactive approach. | Ongoing with co-operation between representatives of County Executive Committee and Club Aontroma. Consideration being given to appointing a marketing company to assist with this. Sponsorship secured for leagues plus another Race Day to be run in 2008 due to its success in 2007. |
| County Executive | 37 a | County Teams | Player Support: Provide the best possible management systems for our county teams. Identify gaps in our setup (individual training programmes, diet requirements, physiology, strength & conditioning etc). | Ongoing. A specific member of county management committee appointed to liaise with each of the county teams apart from county minor hurlers. Regular communication with management teams now occurs. Reviews carried out by all county management teams at the end of season with representatives of County Executive Committee. |
| County Executive | 37 b | County Teams | Management: Establish selection recruitment and interview procedures to be applied when appointing future managers at all levels. Set up interview panels with adequate expertise to assess candidates with particular awareness of continuous experience. | Completed and implemented last year when senior hurling and football managers were appointed. |
| County Executive | 37 c | County Teams | Training: Establish a proper training regime for our county teams with support facilities to cater for all our teams’ needs. Draft a code of conduct/agreement that will clearly outline the players’ benefits and responsibilities. Establish procedures with fast and efficient lines of communication to and from Executive. | Training facilities continuously under review. No progress on Code of Conduct. Fast and efficient lines of communication have been established to and from County Executive Committee. |
| County Executive Committee Chairs | 37 d | County Teams | Committees: Review the roles of football and hurling committees with a view to establishing mechanisms to better promote both codes. | Football and Hurling Committees abolished. Ongoing review of better mechanisms to promote both codes. |

| Led by Group | Page in SP | Themes | Action | Progress |
| --- | --- | --- | --- | --- |
| * Team Managements | 37 e | County Teams | Recruitment: Develop a scouting network for all levels in both codes. | At present players for under age county teams are identified through trials and they are open to everyone. More formal procedures need to be implemented and proposals are now being considered. |

*This had been assigned to Marketing and PR Committee and Club Aontroma in error.

Chontae Aontroma

November 2007